## 04-10
Project Name : Front and Rear Emergancy Breaking System
Suject: MOM
Date 04/10/21
Sr. No. | Name of member | Present | Discussion | To Do Task | Completed | Remark
1 | Pravin Sonne (Product Owner) | Yes |  | Search and download the IEEE paper | Yes
2 | Rashmi Patil (Scrum master) | Yes |  | Download the IEEE paper | Yes | Not feeling well(hospitalized)
3 | Mayur Salunkhe | Yes | first we all search and | Search and download the IEEE paper | Yes
4 | Rupali Musale | Yes | download the IEEE paper | Search and download the IEEE paper | Yes
5 | Moshin Kazi | Yes |  | Search and download the IEEE paper | Yes
6 | Dasharath Nikam | Yes |  | Search and download the IEEE paper | Yes

## 05-10
Project Name : Front and Rear Emergancy Breaking System
Suject: MOM
Date 05/10/21
Sr. No. | Name of member | Present | Discussion | To Do Task | Completed | Remark
1 | Pravin Sonne (Product Owner) | Yes |  | Dangerous obstacle ahead with in the same lane | Yes
2 | Rashmi Patil (Scrum master) | Yes | first group find the requirement | Not feeling well | yes | Not feeling well(hospitalized)
3 | Mayur Salunkhe | Yes | of front breaking system and | leading car applied break suddenly that time emergency break apply | Yes
4 | Rupali Musale | Yes | second group find the requirements | Distance calculation of object at reverse of car At parking place | Yes
5 | Moshin Kazi | Yes | of rear breaking system. | At traffic place driver required sudden break | Yes
6 | Dasharath Nikam | Yes | at least one requirement we have to find | any person or obstacle is come to in front of car in runing condition | Yes
|  |  |  | that time emergancy break applied | Yes

## 06-10
Project Name : Front and Rear Emergancy Breaking System
Suject: MOM
Date 06/10/21
Sr. No. | Name of member | Present | Discussion | To Do Task | Completed | Remark
1 | Pravin Sonne (Product Owner) | Yes |  | Study in detail of all that requirement | Yes
2 | Rashmi Patil (Scrum master) | Yes | Study in detail of all that requirement | and Make A requirement format | yes | Not feeling well(hospitalized)
3 | Mayur Salunkhe | Yes | and Make A requirement format | first group find the requirement in detail | Yes
4 | Rupali Musale | Yes | in Excel sheet or word file of Front and | of front breaking system and | Yes
5 | Moshin Kazi | Yes | Rear Emergency Braking system | second group find the requirements indetail | Yes
6 | Dasharath Nikam | Yes |  | of rear breaking system. | Yes
at least one requirement we have to find

## 07-10
Project Name : Front and Rear Emergancy Breaking System
Suject: MOM
Date 07/10/21
Sr. No. | Name of member | Present | Discussion | To Do Task | Completed | Remark
1 | Pravin Sonne (Product Owner) | Yes |  |  | Yes
2 | Rashmi Patil (Scrum master) | Yes | Study in detail of all that requirement | Study in detail of all that requirement | yes | Not feeling well(hospitalized)
3 | Mayur Salunkhe | Yes | and Make A requirement format | and Make A requirement format | Yes
4 | Rupali Musale | Yes | in Excel sheet or word file of Front and | in Excel sheet or word file of Front and | Yes
5 | Moshin Kazi | Yes | Rear Emergency Braking system | Rear Emergency Braking system | Yes
6 | Dasharath Nikam | Yes |  |  | Yes

## 08-10
Project Name : Front and Rear Emergancy Breaking System
Suject: MOM
Date 08/10/21
Sr. No. | Name of member | Present | Discussion | To Do Task | Completed | Remark
1 | Pravin Sonne (Product Owner) | Yes |  |  | Yes
2 | Rashmi Patil (Scrum master) | Yes | As per our discussion, | Made Requirements in word format | Yes | Not feeling well(hospitalized)
3 | Mayur Salunkhe | Yes | To Make Requirements in word format | for our Project of Front and | Yes
4 | Rupali Musale | Yes | for our Project of Front and | Rear Emergency Braking system | Yes
5 | Moshin Kazi | Yes | Rear Emergency Braking system |  | Yes
6 | Dasharath Nikam | Yes |  |  | Yes

## 09-10
Project Name : Front and Rear Emergancy Breaking System
Suject: MOM
Date 09/10/21
Sr. No. | Name of member | Present | Discussion | To Do Task | Completed | Remark
1 | Pravin Sonne (Product Owner) | Yes |  |  | Yes
2 | Rashmi Patil (Scrum master) | Yes | As per our discussion, |  | Yes
3 | Mayur Salunkhe | Yes | To Find the Input Output Parameter of | To Find the Input Output Parameter of | Yes
4 | Rupali Musale | Yes | for our Project of Front and | for our Project of Front and | Yes
5 | Moshin Kazi | Yes | Rear Emergency Braking system | Rear Emergency Braking system | Yes
6 | Dasharath Nikam | Yes |  |  | Yes